IMPLEMENTATION MILESTONES & EFFORT PLAN

MAYA_X_2.0 — Premium Talent Platform

Derived from the approved SRS, PRD, Enterprise Architecture, Database Design, and REST API Specification

Document Version: 1.0 (Draft)

Date: 20 July 2026

Prepared by: Lead Software Architect

Notice: Effort estimates are given as engineer-weeks (one engineer-week = one engineer, one week) rather than calendar time, since team size/composition was not specified anywhere in the SRS/PRD. Convert to calendar duration by dividing total engineer-weeks per milestone by the number of engineers who can work it in parallel — capped by the Dependencies column.

## Table of Contents

# 1. Estimation Approach

| Aspect | Approach |
| --- | --- |
| Unit | Engineer-weeks (1 engineer × 1 week of focused work), not calendar weeks — team size is not specified anywhere in the source materials |
| Scope basis | MVP scope per PRD §8 (Must-have features) is the primary sequence; Should/Could-have and Future Roadmap items are separate, later milestones |
| Assumed team shape | 1 backend engineer (NestJS), 1 frontend engineer (Next.js), shared/rotating QA and DevOps — ASSUMPTION, since no team composition was provided; re-baseline all estimates once actual team size is known |
| What's excluded | Design (Figma/visual design production) and content/copywriting are not estimated here — this plan covers engineering only, picking up from the Design System (already delivered) as a ready input |
| Confidence | ±40% per milestone — typical for pre-sprint-planning estimates on a project with several SRS Open Questions still unresolved (flagged per milestone below) |

# 2. Milestone Breakdown

## M0 — Foundations & Environment Setup

Monorepo scaffolding, CI/CD skeleton, shared config packages, Docker Compose for local dev, staging/production environments provisioned — the prerequisite for every later milestone (see companion Monorepo Layout document).

| Key Deliverables | • Repository structure per Monorepo Layout doc (apps/, packages/, infra/) • CI pipeline (lint → test → build) running on every PR • Local Docker Compose (Postgres, Redis) working end-to-end • Staging environment reachable on AWS/Vercel |
| --- | --- |
| Dependencies | None (first milestone) |
| Effort Estimate | 3–4 engineer-weeks |

## M1 — Identity & Access (Authentication)

Customer + Admin registration/login, JWT + refresh token issuance/revocation, password reset — unlocks every subsequent module, since almost all other endpoints require an authenticated actor.

| Key Deliverables | • users, admin_users, user_credentials, refresh_tokens, password_reset_tokens tables live (Database Design §3.1) • POST /auth/register, /auth/login, /auth/admin/login, /auth/refresh, /auth/logout, /auth/password-reset/* endpoints (API Spec §2) • AuthGuard + RolesGuard middleware operative for all protected routes |
| --- | --- |
| Dependencies | M0 |
| Effort Estimate | 4–5 engineer-weeks |

## M2 — Talent Catalog

Talent profiles, categories, media library — the content that must exist before Booking (M3) can be demoed or tested end-to-end.

| Key Deliverables | • talents, talent_categories, talent_category_map, media_assets tables live • Public GET /talents, /talents/{slug}, /categories (API Spec §4.1) • Admin talent CRUD + media upload to Cloudinary (API Spec §4.2) • Full-text search (search_vector) operative for FR-09 |
| --- | --- |
| Dependencies | M0, M1 (Admin auth required to manage talent) |
| Effort Estimate | 5–6 engineer-weeks |

## M3 — Booking (Core Transaction)

The platform's core value: Guest/Member booking submission, Agency review queue, status lifecycle, and customer-facing status visibility. This is the single most business-critical milestone.

| Key Deliverables | • booking_requests, booking_status_history tables live • POST /booking-requests (Guest + Member), GET /me/bookings, GET /booking-requests/{id} • Admin queue: GET /admin/booking-requests, PATCH .../status (state machine per Architecture §7.1) • Wishlist (users↔talents) as a light add-on once Booking's data patterns are in place |
| --- | --- |
| Dependencies | M1, M2 |
| Effort Estimate | 6–7 engineer-weeks |

## M4 — Admin Core (Dashboard & Operations)

The Admin Panel shell that makes M2/M3's data operable day-to-day: dashboard summary, and the left-rail navigation/UI shell that later milestones (Membership, Payment, Notification) plug into.

| Key Deliverables | • GET /admin/dashboard/summary • Admin Panel UI shell (left-rail nav, auth-gated routing, noindex) per Design System §10 • Admin role/permission scaffolding (roles, admin_user_roles) even if only one role is used at launch |
| --- | --- |
| Dependencies | M1, M2, M3 (dashboard surfaces data from both) |
| Effort Estimate | 3–4 engineer-weeks |

## M5 — Membership & Payment (Razorpay)

Membership plan browsing/purchase and Razorpay integration. Scoped as a single milestone because payment and membership are tightly coupled in the current design (Database Design §3.4/§3.5).

| Key Deliverables | • membership_plans, subscriptions, payments, coupons, coupon_redemptions tables live • GET /membership-plans, POST .../subscribe, POST /payments/orders, POST /payments/webhook (signature-verified) • Admin membership/coupon/payment management endpoints |
| --- | --- |
| Dependencies | M1 (requires authenticated customer); benefits from M3 patterns but not blocked by it |
| Effort Estimate | 5–7 engineer-weeks |

OPEN QUESTION: M5's estimate carries the widest uncertainty band in this plan. It assumes membership tiers/pricing/benefits are finalized (SRS §10 open question) and that booking-linked payment stays out of scope (SRS §14 open question) before this milestone starts. If booking-linked payment is confirmed in scope, add an estimated 3–4 engineer-weeks and move part of this milestone after M3.

## M6 — Notifications

Event-driven notification dispatch (booking status changes, membership events, payment events) — cuts across M3 and M5, so it is sequenced after both produce events to notify on.

| Key Deliverables | • notification_templates, notifications tables live • Queue-backed dispatch worker (Architecture §9) • Email channel integration (MVP baseline) wired to Booking (M3) and Membership (M5) events • GET /me/notifications, GET /admin/notifications |
| --- | --- |
| Dependencies | M3, M5 (needs their domain events to fire against) |
| Effort Estimate | 3–4 engineer-weeks |

OPEN QUESTION: Estimate assumes a single channel (email). Add 1–2 engineer-weeks per additional channel (SMS/WhatsApp/push) once SRS §13's open question on channels is resolved.

## M7 — Reporting, Analytics & Coupons polish

Lower-priority (Should/Could, per PRD §5) Admin reporting and analytics, plus any coupon UX polish not already covered in M5.

| Key Deliverables | • GET /admin/reports/{type}, GET /admin/analytics/summary • Coupon admin UI polish, redemption reporting |
| --- | --- |
| Dependencies | M3, M5, M6 (reports read across all of them) |
| Effort Estimate | 3–5 engineer-weeks |

ASSUMPTION: Per PRD §8.2, Analytics can rely on a third-party tool (e.g., Google Analytics) at MVP launch, which would remove this milestone's analytics half entirely and cut this estimate roughly in half — confirm before scheduling.

## M8 — SEO, Performance & Accessibility Hardening

Cross-cutting hardening pass across all customer-facing pages built in M2–M6: SSR/ISR tuning, meta tags/sitemap, Core Web Vitals, and the accessibility baseline (SRS §17/§18).

| Key Deliverables | • SSR/ISR rendering strategy applied per page type (Architecture §2.1) • Sitemap.xml, robots.txt, structured data on talent profiles • WCAG 2.1 AA pass on public + account pages (pending client confirmation this is required — SRS §18) |
| --- | --- |
| Dependencies | M2, M3, M5 (needs the pages to exist first) |
| Effort Estimate | 3–4 engineer-weeks |

## M9 — QA, Security Review & Launch Prep

End-to-end test pass, security review (SEC-01 through SEC-09), load/performance validation, production cutover.

| Key Deliverables | • E2E test suite covering booking, membership, and admin review flows • Security review sign-off (auth, payment webhook verification, RBAC) • Production deployment runbook executed (Architecture §10) |
| --- | --- |
| Dependencies | All prior milestones |
| Effort Estimate | 3–5 engineer-weeks |

# 3. Dependency Diagram

Mermaid source (also suitable for direct rendering in project tooling that supports Mermaid, e.g., a wiki or the companion Design System artifact):

flowchart LR

M0[M0 Foundations] --> M1[M1 Identity & Access]

M0 --> M2[M2 Talent Catalog]

M1 --> M2

M1 --> M3[M3 Booking]

M2 --> M3

M1 --> M4[M4 Admin Core]

M2 --> M4

M3 --> M4

M1 --> M5[M5 Membership & Payment]

M3 --> M6[M6 Notifications]

M5 --> M6

M3 --> M7[M7 Reporting/Analytics]

M5 --> M7

M6 --> M7

M2 --> M8[M8 SEO/Performance/A11y]

M3 --> M8

M5 --> M8

M4 --> M9[M9 QA/Security/Launch]

M6 --> M9

M7 --> M9

M8 --> M9

Figure 3.1 — Milestone dependency graph

## 3.1 Critical Path

M0 → M1 → M3 → M4/M5 → M6 → M9. M2 (Talent Catalog) can proceed in parallel with the tail end of M1 once auth scaffolding (not full auth polish) exists, since it mainly needs Admin-authenticated write access. M7 and M8 are the most schedule-flexible milestones — both can compress or be partially deferred to a fast-follow release without blocking launch, per PRD §8's MVP/deferred split.

# 4. Summary Table

| Milestone | Depends On | Effort (engineer-weeks) | PRD MVP Status |
| --- | --- | --- | --- |
| M0 — Foundations | — | 3–4 | Prerequisite (not a feature) |
| M1 — Identity & Access | M0 | 4–5 | MVP (Must) |
| M2 — Talent Catalog | M0, M1 | 5–6 | MVP (Must) |
| M3 — Booking | M1, M2 | 6–7 | MVP (Must) |
| M4 — Admin Core | M1, M2, M3 | 3–4 | MVP (Must) |
| M5 — Membership & Payment | M1 | 5–7 | Deferred fast-follow (PRD §8.2) |
| M6 — Notifications | M3, M5 | 3–4 | MVP for Booking events (Must); Membership events follow M5 |
| M7 — Reporting/Analytics | M3, M5, M6 | 3–5 | Could-have (PRD §5) |
| M8 — SEO/Performance/A11y | M2, M3, M5 | 3–4 | MVP for SEO baseline (Must); A11y depth pending confirmation |
| M9 — QA/Security/Launch | All | 3–5 | Required for any launch |

Total: approximately 38–51 engineer-weeks across all milestones. With the assumed 2-engineer core team (§1) working M2/M3 somewhat serially and M5/M7/M8 partly in parallel where dependencies allow, this maps to roughly 20–28 calendar weeks (5–7 months) to full scope — narrower if Membership/Payment (M5) and Reporting (M7) are deferred past initial launch per the PRD's MVP recommendation, which would bring the MVP-only path (M0–M4, M6 Booking-events, M8 SEO baseline, M9) to roughly 27–35 engineer-weeks.

ASSUMPTION: These totals will shift materially once (a) actual team size/composition is known, and (b) the SRS Open Questions flagged throughout this plan (membership structure, booking-linked payment, notification channels, Admin role subdivision) are resolved. Re-run this estimate after sprint-zero planning with the assigned team.

End of Document.